## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Kumar Manglam | 2025-11-02 | Login was successful but token was not returned | Sprint 1 | Kumar Manglam | Functional | Fixed JWT configuration in backend | 2025-11-03 | Closed | Login working properly
2 | Kumar Manglam | 2025-11-04 | Uploaded files not visible after upload | Sprint 1 | Kumar Manglam | Configuration | Corrected media path settings | 2025-11-05 | Closed | Issue resolved
3 | Kumar Manglam | 2025-11-08 | OCR did not extract name correctly for some cards | Sprint 2 | Kumar Manglam | Functional | Improved OCR handling logic | 2025-11-09 | Closed | Accuracy improved
4 | Kumar Manglam | 2025-11-10 | Aadhaar number validation failed for valid input | Sprint 2 | Kumar Manglam | Logic | Fixed checksum validation code | 2025-11-11 | Closed | Validation working
5 | Kumar Manglam | 2025-11-14 | YOLO model failed to load during analysis | Sprint 3 | Kumar Manglam | Technical | Updated model path and dependencies | 2025-11-15 | Closed | Model loaded successfully
6 | Kumar Manglam | 2025-11-16 | Fraud detection showing false alerts | Sprint 3 | Kumar Manglam | Performance | Adjusted detection threshold | 2025-11-17 | Closed | Results more accurate
7 | Kumar Manglam | 2025-11-20 | Dashboard count not updating correctly | Sprint 4 | Kumar Manglam | UI | Fixed API response mapping | 2025-11-21 | Closed | Dashboard stable
8 | Kumar Manglam | 2025-11-22 | Exported Excel file missing some fields | Sprint 4 | Kumar Manglam | Functional | Updated export logic | 2025-11-23 | Closed | Export correct
9 | Kumar Manglam | 2025-11-28 | CORS error while testing deployment | Sprint 5 | Kumar Manglam | Configuration | Updated CORS settings | 2025-11-29 | Closed | Deployment working